Open Government Partnership

Access to Information Working Group

2016 Work Plan

The main aims of the Access to Information Working Group (ATI WG) are:

- To be a resource for OGP governments in designing and implementing effective and ambitious commitments regarding ATI and disclosure of relevant information;

- To support the participation of key stakeholders, such as ATI oversight agencies, records managers, and civil society in the OGP ATI dialogue;

- To advance the peer learning network of governments, with particular focus on cohort countries and engaging mentors and working group experts; and

- To promote the right of access to information as a catalyst for engaging and informing the public, building more open institutions and ensuring greater government accountability.

## Purpose and objectives

The right of access to information is at different stages in different jurisdiction, and its legal development and implementation vary widely internationally.  Cognizant of these considerable variances and the particular needs of each OGP country, the ATI WG will look to engage at key moments in the fulfillment of five purposes:

- To support governments that are developing their commitments or making new commitments around access to information. The ATI WG will promote the adoption of ambitious commitments that advance the national ATI agenda and lead to greater transparency and openness.

- To promote an inclusive dialogue where multiple stakeholders, particularly ATI oversight bodies, records managers, and civil society leaders, participate in the OGP national process (from consultation to evaluation) and actively engage in permanent national dialogue mechanisms.

- To place particular emphasis on advancing the peer learning network of four identified countries (Liberia, Sierra Leone, Guatemala and Honduras), offering the support of mentor countries and working group experts.

- To identify transversal issue(s) impacting the effective right of access to information and to provide white papers, consensus-building, and recommendations.

- To serve as a resource and support for government agencies and civil society groups that are trying to fulfill their ATI-related commitments, including through relevant research and scholarship.

## Deliverables and Proposed Activities for 2016

The following provides an ambitious and comprehensive set of deliverables and activities.  The engagement of these activities and achievement of the deliverable is dependent upon the active participation of ATI Working Group members and sufficient funding/resources.

- Review new draft commitments related to access to information and support multiple stakeholders in formulating action plans

Date: Present - December

In support of Objective 1 to promote ambitious action plans, the ATI Working Group will offer assistance to relevant OGP countries by reviewing draft commitments, supporting the development of actions plan that advance implementation, and encouraging multi-stakeholder engagement.  Activities may include:

- Writing to all relevant Points of Contact (POCs) to notify them of potential support from the ATI Working Group

- Revising Directory of past and present ATI Commitments, including relevant sections of the IRM reports

- Sharing the draft commitments and action plans directly  with ATI Working Group members from the relevant countries, encouraging their comments and active engagement in developing and finalizing ATI commitments

- Providing comments and suggestions to the POC and civil society partners related to ATI commitments, including  evaluation of  the importance of fulfilling particular commitments and any potential challenges in so doing

- Promoting additional ATI commitments to be included in the national plans

- Uploading to the OGP ATI Working Group web page all draft action plans received by the working group for comment and any analysis provided

## Participate in National, Regional and International OGP Events to promote an inclusive dialogue and encourage emphasis on the role of access to information as a cornerstone of an open and transparent government that promotes public participation

Date: Present - December

## Objective 2 of the working group speaks to the importance of an inclusive dialogue and the active engagement of the ATI Working Group to promote the right of access to information as central to the foundation of the OGP.   In support of this deliverable, activities may include:

- Notifying members of upcoming activities and encouraging participation, such as for the African Regional Meeting scheduled for May 2016 in South Africa and the Americas Regional Plan in Uruguay for the end of May 2016

- Participating in POC meetings to share the value of ATI commitments

- Sending letters of introduction to each POC with names of ATI working group members from their country to facilitate collaboration between them

- Supporting civil society engagement at national OGP meetings, including ATI Working Group members convening in-country meetings

- Organizing ATI Working Group panels or speakers for key events, with a particular focus on the potential positive impact that the awareness, implementation, and exercise of ATI may have on other components of Open Government

- Encourage discussion and development of OGP ATI commitment that link to the Sustainable Development Goals

- Preparing, in collaboration with the World Bank,  ATI Working Group webinar(s)

## Encourage and Support Peer Learning Networks

Date: Present-December

A number of OGP countries have sought support from the ATI Working Group as they seek to advance their efforts to pass, implement and enforce access to information regimes.  Concurrently, ATI champions from OGP member states have offered to share experiences and provide mentorship.  In furtherance of ATI Working Group Objective 3, we will seek to provide concrete opportunities for peer exchanges and mentorship for four designated OGP countries (Liberia, Sierra Leone, Guatemala and Honduras) through activities such as:

- Identifying champions and mentors and pairing with cohort countries

- Assisting cohort countries to develop an inventory of support needs

- Organizing regular interactions/discussions for the four cohort countries, mentors and Working Group experts to share experiences, identify challenges, and consider solutions

- Facilitating a study mission of the cohort countries to a mentor OGP country (with Liberia and Sierra Leone going to an English-speaking country and Guatemala and Honduras to a Spanish-speaking country) for learning and exchange of experiences

## Develop and Disseminate Research/Analysis/Relevant Information and Build Consensus on Transversal Issues Impacting the Right of Access to Information

Date:  April - December

The ATI Working Group will support development of new research and analysis related to ATI OGP commitments as well as disseminate additional relevant information among its members, such as IRM reports, research and articles related to access to information and OGP etc.  Additionally, the ATI Working Group will identify transversal issue(s) impacting the effective right of access to information and develop white papers, seek to build consensus, and provide concrete recommendations and share good practices. Activities may include:

- Further development of OGP ATI Working Group website

- Documenting the successful experiences of ATI OGP commitments and sharing on the website, including where access to information has encouraged fulfillment of other open government principles/components

- Support for new research related to OGP ATI commitments and best practices, potentially commissioning papers/analysis, for example, analysis of IRM findings to evaluate ATI performance in OGP countries or a diagnosis of the state of ATI commitments

- Dissemination of IRM reports, particularly related to ATI commitments

- Identifying transversal issues that are negatively impacting the advancement of the right of access to information, such as poor records-management, weak proactive disclosure, and ineffective enforcement, and developing thematic white papers, opening dialogues, and creating/disseminating potential recommendations and promoting good practices

- Inviting scholars and academics to share relevant papers/articles with the ATI Working Group

- Providing updates to ATI Working Group members